- Project Management Plan

- 3-1 Final Project Part Two: Revised Report

- QSO-355 Resource Estimate & Scheduling

- Anne Lankford

- December 13, 2021

Table of Contents

- Introduction

- Purpose

- Background

- Project Approach

- Project Overview

  - Roles and Responsibilities

  - Scope and Schedule – Revised

- Tasks

  - Description – Revised

  - Time

  - Dependencies

- Resources

  - Alignment – Revised

  - Evaluation – Revised

- Risk

  - Sources – Revised

  - Strategies

- Budget – Revised

- Schedule – Revised

- Introduction

A&D High Tech is a technology company that manufactures or sells computer products, accessories, and services to consumers and small businesses. With an increase in adoption of the internet and online media by the competitors of A&D, A&D was losing a significant target market to them. For this purpose, the company needed to switch or add to its sales channel to reacquire its customers. Chris Johnson, A&D High Tech’s technology project manager, who had a track record of completing projects on time and budget, was called to take over the task of going online and was given a targeted completion timeframe for the assignment before the Christmas holidays.

- Purpose

The project plan is to determine whether A&D High Tech can successfully implement an online shop by the holiday season of 2003. The aim is to increase sales and remain competitive by including online sales to increase revenues. The project consists of an agreement between Chris Johnson, the PM, Ted Walter, CEO, Matt Webb, CIO, and other project stakeholders.

- Background

A&D High Tech was started in Lincoln, Nebraska, by Ted Walter in 1988 with his first store. A&D developed made-to-order products that happened to be the first to be introduced into the personal computer industry. A&D implemented its first enterprise resource planning (ERP) system in 1999, using software from J.D. Edwards. This software could be customized to handle the thousands of parts that A&D used in production. With the successful implementation of the ERP system, A&D High Tech decided to improve its systems in “handling the supply chain, payment process, customer relationship management (CRM), and order management (Jeffery, 2017).” This resulted in an immediate return on investment benefits in the supply chain and data warehousing projects and reduced overall costs. A&D High Tech needs to move towards the next big adventure of operating an online store.

- Project Approach

Ted Walter (the founder/owner) and Jeff White, the Vice President of sales, approved the project to create an online store in early 2002 and gave the okay to CIO Matt Webb. Matt Webb’s first hurdle was to decide on “build vs. buy.” A&D could use a custom-developed program to build a commercial application to meet all of their requirements, or they could purchase a “commercial off-the-shelf (COTS)”  software. The COTS may not meet all of their specific formats, input processes, or elements needed to make it work for A&D directly. Establishing business requirements for the new software, including new orders, additional orders, changes to the order, order status, and lead capture, became eminent. A custom build was the only solution. The benefit to creating a custom build was to gain a strategic IT advantage that would separate them from the competition. This will also allow for flexible options that the COTS cannot. Although there may be hidden costs associated with custom builds, the pros outweighed the cons.

# Project Overview

A&D High Tech is a regional player developing an online distributorship on a national scale through a virtual store. This section will include a Stakeholder Register showing key project roles and responsibilities and a defined project scope. A schedule of tasks will provide the layout of the project.

- Roles and Responsibilities

- Scope and Schedule – Revised

Scope:

The project aims to build an online shop increasing sales and accessing a more extensive consumer base. The scope and business requirements of the online store included new orders, add-on orders, order amends, order status, and lead capture with the following capabilities (Jeffery, 2017):

- Configuration and pricing

- Delivery date based on standard lead times

- Real-time payment processing

- 100 percent validation of required data

- Collection of prospect data about customers

- Integration to back-end (ERP) for manufacturing and order management

The start date has been designated for May 2003, with a completion date of November 2003 by the beginning of the holiday season. Holiday promotional bundles have been added to the scope of work, in an attempt to gain an additional 10% increase in sales as was identified by the VP of marketing.

Schedule:

A&D HighTech’s CEO, Ted Walter, and CIO, Matt Webb, have requested this project the priority over all other projects to ensure it is completed on time for the upcoming holiday season. The project is estimated to take 127 days to complete. This includes gathering data & business requirements, designing flow, developing software requirements, design, testing, creating technical infrastructure, deployment, and project wrap-up. The additional scope of work with the promotional bundles will add three more weeks to the project to configure the site server. The company will have to outsource this task to Microsoft via consultants and/or developers.

# Tasks

A work breakdown structure (WBS) is a tool that lays out everything you must accomplish to finish a project, organizes these tasks into multiple levels, and display these elements visually. The WBS defines all the tasks you need to achieve to complete the project — and the order in which you need to do them.

- Description – Revised

- Time

Time estimates are the backbone for determining deadlines for delivery and planning of projects and will impact people’s assessment of your reliability and competence as a project manager. A delay in one task could result in multiple delays and scope creep due to dependencies. This could have a detrimental impact on the overall project.

- Dependencies

This section has been added to the WBS Resource Alignment document added under the resource section of the report.

# Resources – Revised

Providing allocation of each task to resources once the WBS is finished for a project is extremely useful in assisting project managers in ensuring resources are allocated appropriately and not having too many or too few task functions assigned. Additional resources will be needed to complete the promotional bundles that were added to the scope of work. The current developers are already assigned to a specific task and are not available for additional duties, as a result, it will be necessary to hire outside consultants from Microsoft to handle the work overflow.

- Alignment – Revised

- Evaluation – Revised

There appear to be adequate resources available to complete the project on time based on the provided information. The WBS contains uncertain information as the developers have yet to be determined as the defined sections for many tasks. Among other duties, development and unit testing are the responsibility of the three developers under Marc Sanders, the Development Lead. A significant milestone in developing the software to meet the business requirements. This will be a substantial risk if these developers are not identified whether in-house or contracted. There are additional risk potentials that have been identified due to the changes that have been made to the scope, budget, and timeline. Because of the increased time to complete the ERP interface, the addition of the holiday bundles, and the project is 20% behind schedule – the most prudent solution is to hire an additional developer from Microsoft (Jeffery et al., 2009).

# Risk

The risk management plan is developed to create a mitigation plan on the available methods or resources to remove or reduce the issues. Identifying risks and eliminating them is the project manager’s responsibility or the risk team. The project risk management plan gives members of the project management team a sense of the risk managing actions they can take to identify, analyze, and respond to threats around and within the project. The risk mitigation plan is a subsidiary plan in the hierarchy of the project management plan. The risk in projects can be different depending on the scale of each project and progress through the project life cycle. Below is a risk chart for the risk/strategy for A&D High Tech Online Store.

- Sources – Revised

- Strategies

This section has been added to the Risk Register document under the sources section of the Risk report.

# Budget – Revised

The most important aspect of a budget in project management is the deciding factor of the financial outcome of the project. A Project Budget revolves around the total monetary resources allocated to complete project goals and or objectives within the project. Project budget management aims to estimate and control project costs within the approved budget and achieve the project’s stated goals (MyMG, 2021). In an attempt to keep the scope creep to a minimum and keep costs from getting too far out of control, it was determined that hiring a Microsoft consultant at a rate of $500 per hour for two to three days of work would be the most beneficial solution. The consultant would also require two weeks of lead time to get scheduled. The total cost would estimate an additional $52,000.00 (Jeffery et al., 2009). In the case of A&D High Tech, the information provided in the case study was used to develop the budget estimate based on person-hours per each team member involved. See Budget Spreadsheet listed below:

- Schedule and Gantt Chart – Revised

The Gantt chart gives a visual representation of the project from start to finish. It allows all stakeholders to get a clear picture of all of the steps involved and where the project is at during any given moment. Once you have your schedule in the Gantt chart, you can track the progress of your project. Because this is a visual timeline, it is easier to stay on track and ensure that your project is completed on time.

References

Gilmore, N. (2016, August 15). The purpose & benefits of Gantt charts: Teamgantt. Retrieved December 02, 2021, from https://www.teamgantt.com/blog/10-benefits-of-using-a-gantt-chart-of-your-next-project

Gold, V. (2018, May 23). Three aspects to consider when compiling a project budget. Retrieved from https://www.celoxis.com/article/3-aspects-to-consider-when-compiling-a-project-budget

Jeffery, M. (2017). A&D High Tech (A): Managing Projects for Success. Kellogg School of Management Cases, 1-20. doi:10.1108/case.kellogg.2016.000008

Jeffery, M., Yung, D., & Gershbeyn, A. (2009). A&D High Tech (b): Managing scope change. Kellogg School of Management Cases, 1–7. https://doi.org/10.1108/case.kellogg.2016.000009

MyMG. (2021). 2. Determining Project Budget. Retrieved from https://mymanagementguide.com/guidelines/project-management/cost-management/determining-project-budget/#rsk